## Takt Template
Project Name | [123 empty] | In Collaboration with:
Updated: 07/08/21
[17 empty] | 2021 | [51 empty] | 2022 | [51 empty] | 2023 | [51 empty] | 2024
[8 empty] | Cold Winter Months | [51 empty] | Cold Winter Months | [52 empty] | Cold Winter Months | [51 empty] | Cold Winter Months | [52 empty] | Cold Winter Months
SEPTEMBER |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  |  | DECEMBER |  |  |  | JANUARY |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  |  | JUNE |  |  |  | JULY |  |  |  | AGUST |  |  |  |  | SEPTEMBER |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  |  | DECEMBER |  |  |  | JANUARY |  |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  | APRIL |  |  |  | MAY |  |  |  |  | JUNE |  |  |  | JULY |  |  |  | AUGUST |  |  |  |  | SEPTEMBER |  |  |  | OCTOBER |  |  |  |  | NOVEMBER |  |  |  | DECEMBER |  |  |  | JANUARY |  |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  | APRIL |  |  |  | MAY |  |  |  |  | JUNE |  |  |  | JULY |  |  |  |  | AUGUST |  |  |  | SEPTEMBER |  |  |  | OCTOBER |  |  |  |  | NOVEMBER |  |  |  | DECEMBER |  |  |  | JANUARY |  |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  | APRIL |  |  |  |  | MAY |  |  |  | JUNE |  |  |  | JULY |  |  |  |  | AUGUST |  |  |  | SEPTEMBER |  |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  | DECEMBER
7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30
Need Help in Reading this Takt Plan?
Scan QR Code Below With Smart Phone Camera
Milestone Summary
Notice to Proceed
Substantial Completion
| Duration (Months) | [6 empty] | 0
ASSUMPTIONS
[30 empty] | Schematic Design | [18 empty] | Submit for Civil permit
[36 empty] | Design Development | [17 empty] | Submit for Early Foundation Package
[49 empty] | Construction Documents | [12 empty] | Submit for Building permit
[58 empty] | GMP Development | [16 empty] | Submit for TI permit
[63 empty] | CONTINGENCY |  |  |  | Exterior Skin Lead Time | [52 empty] | INTERIORS LEGEND
[71 empty] | CONTINGENCY |  |  |  | Elevator Lead Time | [44 empty] | 0 | Remove Reshores
[59 empty] | NTP | [60 empty] | 1 | OH MEPS
[120 empty] | 2 | Framing and Door Frames
[120 empty] | 3 | In-Wall Rough
[120 empty] | 4 | Drywall
[120 empty] | 5 | Tape/Finish
[120 empty] | 6 | Paint
[120 empty] | 7 | MEP Trim
[120 empty] | 8 | Flooring
| Critical Procurement | [118 empty] | 9 | Tile and Base
| Description | [6 empty] | Lead Time (wks) |  |  | Date Needed | [108 empty] | 10 | Accessories
[120 empty] | 11 | Okland Pre-Punch + Clean
[120 empty] | 12 | Owner Punch
[83 empty] | Power On | [5 empty] | Air On | [30 empty] | O | Other
SOIL DISTURBANCE PERMIT
[26 empty] | MAKE SAFE UTILITIES | [93 empty] | INTERIORS LEGEND
[28 empty] | MOBILIZATION | [91 empty] | 0 | Remove Reshores
[30 empty] | EXCAVATION | [89 empty] | 1 | Wall Layout + Top Track
[31 empty] | SHORING | [88 empty] | 2 | Fire Sprinkler + Priority Walls
[33 empty] | PIERS | [86 empty] | 3 | OH Ductwork
[37 empty] | FOOTINGS | [82 empty] | 4 | OH Branch Conduits and Lighting Circuits
[37 empty] | STEM/RETAINING WALLS | [32 empty] | Lobby Finishes | [49 empty] | 5 | OH Mechanical Piping
[38 empty] | STEM/RETAINING WALLS | [81 empty] | 6 | OH Electrical
[37 empty] | UG MEP |  |  |  |  | Basement SOG P1 | [77 empty] | 7 | Wall Framing
[38 empty] | UG MEP |  |  |  |  | Basement SOG P2 | [76 empty] | 8 | In wall Rough-in
[42 empty] | Deck L2 Pour 1 | [5 empty] | 1 | 2 | 3 | 3 | 4 | 4 | 5 | 5 | 6 | 6 | 7 | 7 | 8 | 8 | 9 | 10 | 11 | 11 | 12 | 12 | 13 | 14 | 15 | 16 | 17 | 17 | 18 | 18 | 19 | 20 | 21 | 22 | [40 empty] | 9 | Soffits + Ceilings
| Risks | [118 empty] | 10 | Soffit & Ceiling Rough
[120 empty] | 11 | Drywall
[48 empty] | 1 | 1 | 1 | 2 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 10 | 10 | O | O | 11 | 11 | 12 | 12 | [51 empty] | 12 | Taping
[120 empty] | 13 | Prime + First Coat
[116 empty] | SUBSTANTIAL COMPLETION |  |  |  | 14 | Data Cabling
[120 empty] | 15 | Ceiling Grid
[120 empty] | 16 | Casework + Doors
[120 empty] | 17 | MEP Trim / Light and Devices
[120 empty] | 18 | Flooring + Baseboards
[120 empty] | 19 | Final Paint
| Opportunities | [118 empty] | 20 | Final Accessories
[120 empty] | 21 | OCC Pre-Punch & Clean
[43 empty] | UG Coordination | [76 empty] | 22 | Punchlist
Level 1 OH
EXTERIOR SKIN LEGEND
[47 empty] | Level 2 OH | [72 empty] | A | Layout
[120 empty] | B | Exterior Framing
[120 empty] | C | Sheathing
[35 empty] | BIM LEGEND | [84 empty] | D | Air Barrier
[36 empty] | Model Coordination | [83 empty] | E | Punched Openings
| GUIDELINES | [34 empty] | Prepare Shop Drawings + Layout Drawings | [83 empty] | F | Exterior EIFS
| Identify the throughput of the system | [34 empty] | Shop Drawing Approval | [83 empty] | G | Metal Trim
| Identify bottlenecks | [34 empty] | Prefabrication of Material | [83 empty] | H | Fins and Metal Panel
| Check the stagger of areas | [118 empty] | I | Curtain Wall
| Include appropriate buffers | [118 empty] | J | Caulk + Sealants/Paint
| Avoid Christmas & Thanksgiving weeks | [118 empty] | K | Doors + Accessories
| Do day to day planning for work with stacking | [118 empty] | L | Punchlinst
Create phasing visuals and roadblock visual trackers to identify production
| Afternoon huddles daily | [118 empty] | EXTERIOR SKIN LEGEND
| Morning safety huddles to control field ops | [118 empty] | A | Pre-Fab Panels
| Coordinate everything | [94 empty] | Kitchen Equipment and Start-Up | [16 empty] | Weather Contingency | [6 empty] | B | Stick Framing + Sheathing + Waterproofing
| Prefabricate what you can | [113 empty] | Schedule Contingency |  |  |  |  | C | Glazing
| Identify Power On, Conditioned Air, & other key milestones | [86 empty] | Shaft Prep | [31 empty] | D | Masonry
| Consider adding BIM, Prefab, & Commissioning | [90 empty] | Elevator Cabs | [27 empty] | E | Metal Panels
| Consistent layout | [104 empty] | Test + Certification | [13 empty] | F | Finish Parapet Cap
[88 empty] | Erect Stair | [31 empty] | G | Sealants + Testing
| GOALS | [90 empty] | Pour Stair Pans | [27 empty] | R | Roofing
| Find the rhythm of the project | [118 empty] | Z | Flashing + Parapet Cap
| Communicate the schedule on a single page | [88 empty] | Erect Stair
| Spend 90% of time preventing roadblocks | [92 empty] | Pour Stair Pans | [25 empty] | SITEWORK LEGEND
| Obtain geographical control of takt areas | [118 empty] | G | Layout
| Simplify meetings to make work ready and remove roadblocks | [118 empty] | H | Fine Grade
| Immediately see problems | [88 empty] | Pre-Functional Checklists | [29 empty] | I | Concrete
| Hold team accountable | [97 empty] | Controls | [20 empty] | J | Pavers
[104 empty] | TAB | [15 empty] | K | Landscaping
| RULES | [66 empty] | Temp Roof |  |  |  |  | Install Swing Stages | [35 empty] | Commissioning | [10 empty] | L | Punchlist
| If a contractor is not complete, they work Saturday | [75 empty] | Set AHU & Install | [27 empty] | Fire Life Safety
| Nothing hits the floor | [80 empty] | Roofing | [26 empty] | Final Walks
Just in time deliveries and manpower
| No going faster or slower | [70 empty] | A | A | A | A | B | B | B | B | Z | Z | Z | Z | C | C | C | C | D | D | D | D | D | D | D | D | E | E | E | E | E | E | F | F | G | G | G | G
Control your designated area
Everyone onsite has a copy
| Pull contractors behind you | [70 empty] | A | B | B | C | D | D | E | E | F | F | F | F | G | G | H | H | I | I | I | J | K | K | L | L
Remove roadblocks fanatically
[63 empty] | Man & Material Hoist | [37 empty] | G | H | I | I | I | J | K | L | Site Area 1
Tower Crane
[54 empty] | BRANDING | [14 empty] | CHECKLIST
a. Ensure basements/deep ex have adequate physical space and time
[56 empty] | COLOR PALLET: HIDE WHEN DONE | [12 empty] | b. Use trade input or historical production rates for the slowest trades on exterior skin
c. Give time/proper conditions for shoring removal or fireproofing?
d. Show come-back rooms or walls
e. Building should be dried in prior to starting insulation/drywall
[56 empty] | Main Color -> | [12 empty] | f. Show the effect of all critical procurement on construction
g. Show links between major phases, structure, skin, interiors, BIM, etc.
h. 90-Day start-up given time to happen
i. Overall duration has been verified against other projects of similar size/scope
SUGGESTED COLORS FOR A HIGH-LEVEL TAKT
Preconstruction
Site/Foundations
Structure/BIM
MEP Rough-In + Framing
Hang/Taping/Drywall/Grid
Finishes and Furnishings
Exterior Envelope
Commissioning + Punch
Interiors
Some Interior Areas Will Require Multiple Crews
Structure
BIM
Exterior
Some Interior Areas Will Require Multiple Crews

## Takt Guidelines
Takt Startup Guide & Process Tracker: |  |  | Takt Integrity Checklist:
• | Identify your start and end date |  | Does my Takt plan?
| • | Discuss with Business Development what was sold and promised in the interview.
| • | Discuss as a team what duration would be competetive in the local market for this type of building. | Meet the following requirements?
| • | Decide as a team what your preliminary target is. |  | Visual Schedule showing time and space
• | Research your drawings |  |  | Showing work, trade, and logistical flow (When, What, Where)
| • | Read the general notes, front matter, typical details, and one-line diagrams. |  | Scheduled on a rhythm
| • | Research overall project and visualize in 3D. |  | With the appropriate buffers
• | Identify the general flow of the project based on known constraints |  |  | That stabilizes the pace of work with One-Process-Flow & Limiting Work In Process
| • | In what direction will the project flow? |  | With a reasonable overall project duration
| • | Where are the constraints? | Comply with my Takt Schedule Health Metrics?
| • | Where will material access be? |  | The Value Parametric
| • | What areas need to begin first to support MEP infrastructure? |  | The Efficiency Parametric
| • | What horizontal and vertical flows do you have? |  | The Stability Parametric
• | Identify preliminary Takt Zones |  |  | It has Trade buy-in
| • | Draw in preliminary Takt zones based on your best guess. |  | It includes buffers according to the risk analysis
• | Identify preliminary Takt time |  |  | It has the proper percentages of flow
| • | Guess on the Takt time. If you are not sure, choose a 5 day Takt time. |  | >80% for trade flow
• | Pull plan a typical sequence to start |  |  | >60% for workflow
| • | Identify the preliminary Takt zone you want to pull plan by phase. |  | It has all ancillary, infrastructure, and support activities included in it
| • | Send out homework to trades with the conditions of satisfaction. |  | It shows interdependence ties between phases
| • | Perform the pull plan with the trades. |  | It shows critical milestones and where they land in the schedule
• | Create the Takt sequence |  |  | It blocks out Thanksgiving and Christmas as a buffer week.
| • | List the pull plan activities with durations |  | It shows come-back areas
| • | Find the most common Takt time |  | It shows the impact of weather on the Takt plan
| • | Level other items to that Takt time and package them into work steps, work packages, and Takt wagons |  | It was reviewed in a fresh eyes meeting with a group of peers that will make, when combined, over 100 years of experience in the review of your plan before submitting a GMP.
| • | Create the sequence legend | Have a solid?
| • | Create your first representative Takt sequence |  | Rhythm
• | Create the Takt phase |  |  | Continuity
| • | Simulate the Takt phase with the right stagger between sequences |  | Consistency
• | Identify logistics flow |  |  | Overall Duration
| • | Label each Takt sequence with a Takt zone indicator | Obey?
• | Optimize the throughput with Little’s Law |  |  | Little’s Law
| • | Run a simulation of the ideal throughput by using Little’s Law - (TW + TS - 1) * TT = Duration (Throughput Time) |  | The Law of Bottlenecks
• | Network phases together |  |  | The Law of the Effect of Variation
| • | Create other Takt phases |  | Kingman’s Formula
| • | Network them together with interdepence ties |  | Brooks’s Law
| • | Check the logic of your ties and the relationship between phases | Enable you to?
| • | Place all phases with ties into the right time scale according to the start and end date |  | Show it on one page?
• | Develop work steps |  |  | See all three types of flow?
| • | List out work steps for each work package |  | Bring materials JIT?
| • | Estimate the duration of the steps or cycle time |  | Prefabricate on a rhythm?
| • | If there is more cycle time than time in a Takt time, considere leveling work steps to another work package in another Takt time |  | Have Trades control geographical areas?
• | Trigger planning buffers in the system
| • | Identify any high risk features of work in your sequences
| • | Ask yourself what planning, quality preparation or forward checks need to be done for those steps, work packages, or Takt wagons
| • | Enter in work steps into forward Takt times or as a planning buffer Takt wagon to trigger the planning and preparation of the work soon enough to ensure the success of that work
• | Add buffers
| • | Add in the appropriate buffers from the buffer section in the book and perform the parametric calulations in the schedule health section of the book
• | Create standard work
| • | For high risk features of work, create a checklist of FOW board showing visually how crews should install the scope of work
• | Identify bottlenecks
| • | Identify bottlenecks by finding the slowest trade process
• | Verify with trade partners
| • | Teach trades how to understand and visualize the Takt plan
| • | Review the Takt plan with trade and get their buy-in on sequence, trade flow, process times within Takt wagons and the overall plan
• | Create Logistics plan/drawings
| • | Create a logistics plan with all the correct checklist items per the book Elevating Construction Superintendents in the logistics section
• | Create Takt Zone maps
| • | Create Takt zone maps that show the Takt zones per the most current Takt zone outlines after the optimization that was done to identify the right batch sizes
• | Perform a risk analysis
| • | Perform the recommend risk analysis with the team
| • | Adjust throughput times if possible
| • | Communicate the results to all stakeholders
• | Create a Basis of Schedule
| • | Create a basis of schedule
| • | Request input from the entire project team
| • | Review with Estimators and the project manager
• | Align procurement
| • | Align all procurement items to the schedule
| • | Ensure your procurement tracking system is 100% ready to go
• | Review in a fresh eyes meeting
| • | Identify potential risks
| • | Identify potential solutions
| • | Make assignments
| • | Create your stage indicators
| • | Populate your Risk & Opportunity Register with cost and schedule risk amounts and mitigate the risk weekly in team meetings
• | Create roadblock tracking maps
| • | Create a interiors, exterior, and site roadblock tracking maps
| • | Begin using them in all meetings
• | Track historical production
| • | Track historical production rates
| • | Update work steps within the standard Takt wagons on the micro-level schedule
• | Add a TPNR
| • | Identify and visually show your Takt Point of No Return
• | Begin using your Takt plan
• | Update it weekly
• | When modication are needed, ensure your new version complies with the Schedule Health section in the book
• | Review the schedule weekly in the Trade Partner Weekly Tactical
• | Weekly Work Plans are created from work steps weeks
• | Everyone in the field has a copy
• | Takt plan in updated weekly

## Takt Plan - Macro
[95 empty] | Updated: 07/08/21 | [9 empty] | In Collaboration with:
[17 empty] | 2021 | [51 empty] | 2022 | [103 empty] | 2024
[8 empty] | Cold Winter Months | [51 empty] | Cold Winter Months | [104 empty] | Cold Winter Months | [52 empty] | Cold Winter Months
SEPTEMBER |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  |  | DECEMBER |  |  |  | JANUARY |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  |  | JUNE |  |  |  | JULY |  |  |  | AGUST |  |  |  |  | SEPTEMBER |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  |  | DECEMBER |  |  |  | JANUARY |  |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  | APRIL |  |  |  | MAY |  |  |  |  | JUNE |  |  |  | JULY |  |  |  | AUGUST |  |  |  |  | SEPTEMBER |  |  |  | OCTOBER |  |  |  |  | NOVEMBER |  |  |  | DECEMBER |  |  |  | JANUARY |  |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  | APRIL |  |  |  | MAY |  |  |  |  | JUNE |  |  |  | JULY |  |  |  |  | AUGUST |  |  |  | SEPTEMBER |  |  |  | OCTOBER |  |  |  |  | NOVEMBER |  |  |  | DECEMBER |  |  |  | JANUARY |  |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  | APRIL |  |  |  |  | MAY |  |  |  | JUNE |  |  |  | JULY |  |  |  |  | AUGUST |  |  |  | SEPTEMBER |  |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  | DECEMBER
7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30
Milestone Summary
Need Help in Reading this Takt Plan?
| Notice to Proceed | [6 empty] | 2021-05-10 | [7 empty] | Scan QR Code Below With Smart Phone Camera
| Substantial Completion | [6 empty] | 2023-01-05
| Duration (Months) | [6 empty] | 19.8904
ASSUMPTIONS
Critical Procurement
| Description | [6 empty] | Lead Time (wks) |  |  | Date Needed
Risks
Opportunities
GUIDELINES
Identify the throughput of the system
Identify bottlenecks
Check the stagger of areas
Include appropriate buffers
Avoid Christmas & Thanksgiving weeks
Do day to day planning for work with stacking
Create phasing visuals and roadblock visual trackers to identify production
Afternoon huddles daily
Morning safety huddles to control field ops
Coordinate everything
Prefabricate what you can
Identify Power On, Conditioned Air, & other key milestones
Consider adding BIM, Prefab, & Commissioning
Consistent layout
GOALS
Find the rhythm of the project
Communicate the schedule on a single page
Spend 90% of time preventing roadblocks
Obtain geographical control of takt areas
Simplify meetings to make work ready and remove roadblocks
Immediately see problems
Hold team accountable
RULES
If a contractor is not complete, they work Saturday
Nothing hits the floor
Just in time deliveries and manpower
No going faster or slower
Control your designated area
Everyone onsite has a copy
Pull contractors behind you
Remove roadblocks fanatically

## Takt Plan - Norm
2022
| May |  |  |  | June |  |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  |  | December |  |  |  | January |  |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December
26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25

## Takt Plan - Micro
1
2
3
4
5
1
| ASSIGNMENT DESCRIPTION Criteria for release of assignments Defined - Sound - Proper Sequence - Right Size - Able to Learn | MANPOWER (# of Crews/ Crew Size) | ORGANIZATION | RESPONSIBLE PARTY | COMMENTS | 1 | 2 | 3 | 4 | 5
2
| ASSIGNMENT DESCRIPTION Criteria for release of assignments Defined - Sound - Proper Sequence - Right Size - Able to Learn | MANPOWER (# of Crews/ Crew Size) | ORGANIZATION | RESPONSIBLE PARTY | COMMENTS | 1 | 2 | 3 | 4 | 5
3
| ASSIGNMENT DESCRIPTION Criteria for release of assignments Defined - Sound - Proper Sequence - Right Size - Able to Learn | MANPOWER (# of Crews/ Crew Size) | ORGANIZATION | RESPONSIBLE PARTY | COMMENTS | 1 | 2 | 3 | 4 | 5
4
| ASSIGNMENT DESCRIPTION Criteria for release of assignments Defined - Sound - Proper Sequence - Right Size - Able to Learn | MANPOWER (# of Crews/ Crew Size) | ORGANIZATION | RESPONSIBLE PARTY | COMMENTS | 1 | 2 | 3 | 4 | 5
5
| ASSIGNMENT DESCRIPTION Criteria for release of assignments Defined - Sound - Proper Sequence - Right Size - Able to Learn | MANPOWER (# of Crews/ Crew Size) | ORGANIZATION | RESPONSIBLE PARTY | COMMENTS | 1 | 2 | 3 | 4 | 5

## WWP
Project Progress
[8 empty] | CATEGORIES OF VARIANCE | [7 empty] | TOTAL ACTIVITIES | 0
[8 empty] | 1 | Contracts/CO's |  |  | 8 | Qualified Staff Availability |  |  | ACTIVITIES COMPLETED | 0
[8 empty] | 2 | Client Change |  |  | 9 | Materials/supplies availability |  |  | PERCENT PLANNED COMPLETE | #DIV/0!
[8 empty] | 3 | Submittals |  |  | 10 | Equipment
[8 empty] | 4 | Arch/Eng/Design/RFI |  |  | 11 | Weather
SITE/AREA | FLOOR | ZONE | ASSIGNMENT DESCRIPTION Criteria for release of assignments Defined - Sound - Proper Sequence - Right Size - Able to Learn | MANPOWER (# of Crews/ Crew Size) | ORGANIZATION | RESPONSIBLE PARTY | COMMENTS | 5 | Equip Availability |  |  | 12 | Site Conditions
[8 empty] | 6 | Prior Work Complete - Others |  |  | 13 | Incorrect Time Estimate
[8 empty] | 7 | Prior Work Complete - Self |  |  | 14 | Off Project Demands
[8 empty] | STARTING ON |  |  |  | Week #
[8 empty] | Mon | Tues | Wed | Thur | Fri | Sat | Sun | DONE? | REASONS FOR VARIANCE | Cate- gory
[8 empty] | 0 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | Y/N
Workable Backlog

## WWP Agenda
Weekly Work Planning Meeting Agenda
1. Review Previous Plus/Delta (1 min.)
2. General, Operational and Safety Concerns (5 min.)
3. Review 6-Week Look-Ahead Plan (15 min.)
a. Review the new week (#6) – Note activities that are starting up in week 6
b. Review weeks 2-5 only by new exceptions that pop up
c. Review constraint log and note any overdue constraints and impact
4. Review Last Week’s Performance (5 min.)
a. Last week’s PPC
b. Current week's PPC
c. Trend Chart
d. Variance Chart
5. Finalize Next Week’s WWP (35 min.)
6. Coordinate Individual Plans for Oﬀ Line Conversations (Parking Lot) (5 min.)
7. General/Round Robin
8. Plus/Delta (2 min.)

## PPCChart
PLAN PERCENT COMPLETE
| Start week |  | 2020-08-24
| Last Planner Wk# | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
| Week | 2020-08-24 | 2020-08-31 | 2020-09-07 | 2020-09-14 | 2020-09-21 | 2020-09-28 | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-10-26 | 2020-11-02 | 2020-11-09 | 2020-11-16 | 2020-11-23 | 2020-11-30 | 2020-12-07 | 2020-12-14 | 2020-12-21 | 2020-12-28 | 2021-01-04 | 2021-01-11 | 2021-01-18 | 2021-01-25 | 2021-02-01 | 2021-02-08 | 2021-02-15 | 2021-02-22 | 2021-03-01 | 2021-03-08 | 2021-03-15
| PPC | 1: #REF!; 2020-08-24 2: #REF!; 2020-08-24 3: #REF!; 2020-08-24 4: #DIV/0!
Note on L6: Zach Dennis: Automatically* pulls PPC data from each indiviual WWP sheet/tab Formula example: ='WWP-8.24'!R5 *Will have to copy/paste this formula over to the right in this row for each new WWP sheet/tab that gets created each week (by adjusting the name/title of the new WWP sheet/tab to reference from). Be sure to use the cell reference "R5" in the formula, not the cell range "R5:R6" that would occur by clicking on the merged cells where this data is found on the referenced WWP sheets/tabs.

## Variance
PROJECT VARIANCE CONTROL
#REF! |  |  |  | Staff Assigned to determine cause | Date Cause Investigation Complete | Equipment
#REF! | [5 empty] | Contracts/CO's | Client Change | Submittals | Arch/Eng/Design/RFI | Schedule/Coordination | Prior Work Complete -- Others | Prior Work Complete - Self | Qualified Staff Availability | Materials/Supplies Availability | Equipment | Weather | Site Conditions | Incorrect Time Estimate | Off-project Demands
#REF!
WWP Date | RESPONSIBILITY | REASON FOR VARIANCE | CATEGORY
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Reason for Variance | count
[20 empty] | Contracts/CO's | 0
[20 empty] | Client Change | 0
[20 empty] | Submittals | 0
[20 empty] | Arch/Eng/Design/RFI | 0
[20 empty] | Schedule/Coordination | 0
[20 empty] | Prior Work Complete -- Others | 0
[20 empty] | Prior Work Complete - Self | 0
[20 empty] | Qualified Staff Availability | 0
[20 empty] | Materials/Supplies Availability | 0
[20 empty] | Equipment | 0
[20 empty] | Weather | 0
[20 empty] | Site Conditions | 0
[20 empty] | Incorrect Time Estimate | 0
[20 empty] | Off-project Demands | 0
TOTAL
Note on D15: Zach Dennis: Automatically* pulls Variance data from each indiviual WWP sheet/tab Formula example: =IF('WWP-8.24'!Q15="","",'WWP-8.24'!Q15) *Will have to copy/paste this formula down for each new WWP sheet/tab that gets created each week (by adjusting the name/title of the new WWP sheet/tab to reference from). Only need to utilize when you have Variances listed within each referenced WWP week sheet/tab. Can overwrite the next rows below this one when you have a Variance to list from the next week's WWP sheet/tab.
Note on E15: Zach Dennis: Automatically* pulls Variance data from each indiviual WWP sheet/tab Formula example: =IF('WWP-8.24'!R15="","",'WWP-8.24'!R15) *Will have to copy/paste this formula down for each new WWP sheet/tab that gets created each week (by adjusting the name/title of the new WWP sheet/tab to reference from). Only need to utilize when you have Variances listed within each referenced WWP week sheet/tab. Can overwrite the next rows below this one when you have a Variance to list from the next week's WWP sheet/tab. TIP #1: To easily create the proper formula in this cell: Use the cell to the left in column D to 'Auto Fill' this cell, by dragging the Fill Handle right over to this cell. Tip #2: After properly creating these two cells in this row (columns D & E), Easily 'Auto Fill' the rest of the rows below: Select both cells in this row (D & E), then drag the Fill Handle down as far as needed until no more Variance data is pulled from the referenced WWP sheet/tab.

## VARChart
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## Roadblocks
ROADBLOCK LOG
| GROUP | #REF!
| PROGRAM | #REF!
| PROJECT | #REF!
| PROJECT NUMBER | #REF!
| RESPONSIBLE INDIVIDUAL | #REF!
CONST # |  | SCHEDULE ID# (IMPACTED TASK) | REQUESTED BY PARTY | DATE IDENTIFIED | DATE NEEDED | PROMISED BY | DATE PROMISED | RFI # | DATE ACTUALLY COMPLETE | COMMENTS
REPEAT | DESCRIPTION
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29

## Plus_Delta
Plus / Delta
Date | Plus | Delta

## Parking Lot
Parking Lot
Project Name:
Date | Issue | People Involved in Follow-Up Discussion | Person Coordinating | Date and Time of Follow-up Discussion | Status