## Takt Template
Project Name
Updated: 04/14/21
[17 empty] | 2021 | [51 empty] | 2022 | [51 empty] | 2023 | [51 empty] | 2024
[8 empty] | Cold Winter Months | [51 empty] | Cold Winter Months | [52 empty] | Cold Winter Months | [51 empty] | Cold Winter Months | [52 empty] | Cold Winter Months
SEPTEMBER |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  |  | DECEMBER |  |  |  | JANUARY |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  |  | JUNE |  |  |  | JULY |  |  |  | AGUST |  |  |  |  | SEPTEMBER |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  |  | DECEMBER |  |  |  | JANUARY |  |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  | APRIL |  |  |  | MAY |  |  |  |  | JUNE |  |  |  | JULY |  |  |  | AUGUST |  |  |  |  | SEPTEMBER |  |  |  | OCTOBER |  |  |  |  | NOVEMBER |  |  |  | DECEMBER |  |  |  | JANUARY |  |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  | APRIL |  |  |  | MAY |  |  |  |  | JUNE |  |  |  | JULY |  |  |  |  | AUGUST |  |  |  | SEPTEMBER |  |  |  | OCTOBER |  |  |  |  | NOVEMBER |  |  |  | DECEMBER |  |  |  | JANUARY |  |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  | APRIL |  |  |  |  | MAY |  |  |  | JUNE |  |  |  | JULY |  |  |  |  | AUGUST |  |  |  | SEPTEMBER |  |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  | DECEMBER
7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30
Milestone Summary
Notice to Proceed
Substantial Completion
| Duration (Months) | [6 empty] | 0
ASSUMPTIONS
[30 empty] | Schematic Design | [18 empty] | Submit for Civil permit
[36 empty] | Design Development | [17 empty] | Submit for Early Foundation Package
[49 empty] | Construction Documents | [12 empty] | Submit for Building permit
[58 empty] | GMP Development | [16 empty] | Submit for TI permit
[63 empty] | CONTINGENCY |  |  |  | Exterior Skin Lead Time | [52 empty] | INTERIORS LEGEND
[71 empty] | CONTINGENCY |  |  |  | Elevator Lead Time | [44 empty] | 0 | Remove Reshores
[59 empty] | NTP | [60 empty] | 1 | OH MEPS
[120 empty] | 2 | Framing and Door Frames
[120 empty] | 3 | In-Wall Rough
[120 empty] | 4 | Drywall
[120 empty] | 5 | Tape/Finish
[120 empty] | 6 | Paint
[120 empty] | 7 | MEP Trim
[120 empty] | 8 | Flooring
| Critical Procurement | [118 empty] | 9 | Tile and Base
| Description | [6 empty] | Lead Time (wks) |  |  | Date Needed | [108 empty] | 10 | Accessories
[120 empty] | 11 | Okland Pre-Punch + Clean
[120 empty] | 12 | Owner Punch
[83 empty] | Power On | [5 empty] | Air On | [30 empty] | O | Other
SOIL DISTURBANCE PERMIT
[26 empty] | MAKE SAFE UTILITIES | [93 empty] | INTERIORS LEGEND
[28 empty] | MOBILIZATION | [91 empty] | 0 | Remove Reshores
[30 empty] | EXCAVATION | [89 empty] | 1 | Wall Layout + Top Track
[31 empty] | SHORING | [88 empty] | 2 | Fire Sprinkler + Priority Walls
[33 empty] | PIERS | [86 empty] | 3 | OH Ductwork
[37 empty] | FOOTINGS | [82 empty] | 4 | OH Branch Conduits and Lighting Circuits
[37 empty] | STEM/RETAINING WALLS | [32 empty] | Lobby Finishes | [49 empty] | 5 | OH Mechanical Piping
[38 empty] | STEM/RETAINING WALLS | [81 empty] | 6 | OH Electrical
[37 empty] | UG MEP |  |  |  |  | Basement SOG P1 | [77 empty] | 7 | Wall Framing
[38 empty] | UG MEP |  |  |  |  | Basement SOG P2 | [76 empty] | 8 | In wall Rough-in
[42 empty] | Deck L2 Pour 1 | [5 empty] | 1 | 2 | 3 | 3 | 4 | 4 | 5 | 5 | 6 | 6 | 7 | 7 | 8 | 8 | 9 | 10 | 11 | 11 | 12 | 12 | 13 | 14 | 15 | 16 | 17 | 17 | 18 | 18 | 19 | 20 | 21 | 22 | [40 empty] | 9 | Soffits + Ceilings
| Risks | [118 empty] | 10 | Soffit & Ceiling Rough
[120 empty] | 11 | Drywall
[48 empty] | 1 | 1 | 1 | 2 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 10 | 10 | O | O | 11 | 11 | 12 | 12 | [51 empty] | 12 | Taping
[120 empty] | 13 | Prime + First Coat
[116 empty] | SUBSTANTIAL COMPLETION |  |  |  | 14 | Data Cabling
[120 empty] | 15 | Ceiling Grid
[120 empty] | 16 | Casework + Doors
[120 empty] | 17 | MEP Trim / Light and Devices
[120 empty] | 18 | Flooring + Baseboards
[120 empty] | 19 | Final Paint
| Opportunities | [118 empty] | 20 | Final Accessories
[120 empty] | 21 | OCC Pre-Punch & Clean
[43 empty] | UG Coordination | [76 empty] | 22 | Punchlist
Level 1 OH
EXTERIOR SKIN LEGEND
[47 empty] | Level 2 OH | [72 empty] | A | Layout
[120 empty] | B | Exterior Framing
[120 empty] | C | Sheathing
[35 empty] | BIM LEGEND | [84 empty] | D | Air Barrier
[36 empty] | Model Coordination | [83 empty] | E | Punched Openings
| GUIDELINES | [34 empty] | Prepare Shop Drawings + Layout Drawings | [83 empty] | F | Exterior EIFS
| Identify the throughput of the system | [34 empty] | Shop Drawing Approval | [83 empty] | G | Metal Trim
| Identify bottlenecks | [34 empty] | Prefabrication of Material | [83 empty] | H | Fins and Metal Panel
| Check the stagger of areas | [118 empty] | I | Curtain Wall
| Include appropriate buffers | [118 empty] | J | Caulk + Sealants/Paint
| Avoid Christmas & Thanksgiving weeks | [118 empty] | K | Doors + Accessories
| Do day to day planning for work with stacking | [118 empty] | L | Punchlinst
Create phasing visuals and roadblock visual trackers to identify production
| Afternoon huddles daily | [118 empty] | EXTERIOR SKIN LEGEND
| Morning safety huddles to control field ops | [118 empty] | A | Pre-Fab Panels
| Coordinate everything | [94 empty] | Kitchen Equipment and Start-Up | [16 empty] | Weather Contingency | [6 empty] | B | Stick Framing + Sheathing + Waterproofing
| Prefabricate what you can | [113 empty] | Schedule Contingency |  |  |  |  | C | Glazing
| Identify Power On, Conditioned Air, & other key milestones | [86 empty] | Shaft Prep | [31 empty] | D | Masonry
| Consider adding BIM, Prefab, & Commissioning | [90 empty] | Elevator Cabs | [27 empty] | E | Metal Panels
| Consistent layout | [104 empty] | Test + Certification | [13 empty] | F | Finish Parapet Cap
[88 empty] | Erect Stair | [31 empty] | G | Sealants + Testing
| GOALS | [90 empty] | Pour Stair Pans | [27 empty] | R | Roofing
| Find the rhythm of the project | [118 empty] | Z | Flashing + Parapet Cap
| Communicate the schedule on a single page | [88 empty] | Erect Stair
| Spend 90% of time preventing roadblocks | [92 empty] | Pour Stair Pans | [25 empty] | SITEWORK LEGEND
| Obtain geographical control of takt areas | [118 empty] | G | Layout
| Simplify meetings to make work ready and remove roadblocks | [118 empty] | H | Fine Grade
| Immediately see problems | [88 empty] | Pre-Functional Checklists | [29 empty] | I | Concrete
| Hold team accountable | [97 empty] | Controls | [20 empty] | J | Pavers
[104 empty] | TAB | [15 empty] | K | Landscaping
| RULES | [66 empty] | Temp Roof |  |  |  |  | Install Swing Stages | [35 empty] | Commissioning | [10 empty] | L | Punchlist
| If a contractor is not complete, they work Saturday | [75 empty] | Set AHU & Install | [27 empty] | Fire Life Safety
| Nothing hits the floor | [80 empty] | Roofing | [26 empty] | Final Walks
Just in time deliveries and manpower
| No going faster or slower | [70 empty] | A | A | A | A | B | B | B | B | Z | Z | Z | Z | C | C | C | C | D | D | D | D | D | D | D | D | E | E | E | E | E | E | F | F | G | G | G | G
Control your designated area
Everyone onsite has a copy
| Pull contractors behind you | [70 empty] | A | B | B | C | D | D | E | E | F | F | F | F | G | G | H | H | I | I | I | J | K | K | L | L
Remove roadblocks fanatically
[63 empty] | Man & Material Hoist | [37 empty] | G | H | I | I | I | J | K | L | Site Area 1
Tower Crane
[54 empty] | BRANDING | [14 empty] | CHECKLIST
a. Ensure basements/deep ex have adequate physical space and time
[56 empty] | COLOR PALLET: HIDE WHEN DONE | [12 empty] | b. Use trade input or historical production rates for the slowest trades on exterior skin
c. Give time/proper conditions for shoring removal or fireproofing?
d. Show come-back rooms or walls
e. Building should be dried in prior to starting insulation/drywall
[56 empty] | Main Color -> | [12 empty] | f. Show the effect of all critical procurement on construction
g. Show links between major phases, structure, skin, interiors, BIM, etc.
h. 90-Day start-up given time to happen
i. Overall duration has been verified against other projects of similar size/scope
SUGGESTED COLORS FOR A HIGH-LEVEL TAKT
Preconstruction
Site/Foundations
Structure/BIM
MEP Rough-In + Framing
Hang/Taping/Drywall/Grid
Finishes and Furnishings
Exterior Envelope
Commissioning + Punch
Interiors
Some Interior Areas Will Require Multiple Crews
Structure
BIM
Exterior
Some Interior Areas Will Require Multiple Crews

## Daily Takt
2020 | [17 empty] | 2021 | [52 empty] | 2022
| September |  |  |  | October |  |  |  | November |  |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  |  | March |  |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  |  | December |  |  |  | January |  |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December
7 |  | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 |  | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25
[26 empty] | A | Layout
[26 empty] | B | Framing [from the outside]
[26 empty] | C | Sheathing
[26 empty] | D | Air Barrier & Flashing
[26 empty] | E | Clips & Prep
[26 empty] | F | Set Scaffold
[26 empty] | G | Metal Trim
[26 empty] | H | Metal Panels (insulation)
[26 empty] | I | Unit Windows (GL-2)
[26 empty] | J | Caulk & Paint
[26 empty] | K | Curtain Wall
[26 empty] | L | Fins and Extruded Metal (louvers where applicable)
[26 empty] | M | Awnings
[26 empty] | N | Pavers
[26 empty] | O | Glass Railing
[26 empty] | P | Masonry
[26 empty] | Q | Storefront
[26 empty] | CM | Clean & Seal
[26 empty] | W | Water Testing
[26 empty] | Z | Final Clean
[26 empty] | R | Punchlist