## Sheet1
Plan, Communicate, & Stabilize
Plan | The Plan - The plan precedes all other aspects of the project - The first planner system
| A1 | Create project strategy
| A2 | Identify constraints (building, Owner, weather, sequence)
| A3 | Incorporate contract requirements, division 1 specs, and other Owner requirements into plan
| A4 | Identify flow, sequence, and breakout areas of project
| A5 | Perform a takt analysis of major phases of project (Foundations, Structure, Exterior, Interiors)
| A6 | Perform a day to day geographical analysis for needed areas
| A7 | Define all work breakdown structures
| A8 | Define activities for each WBS as a sequence - do not try to compress the schedule to fit a pre-determined overall duration.
| A9 | Determine sequence, flow, and create logic ties
| A10 | Perform an analysis on bottle neck activities. Consider using production rates from historical data
| A11 | Schedule in constraints and support systems in schedule (dry-in, air-on, MEP, etc.)
| A12 | Make procurement strategy, add procurement to schedule, and begin procurement meetings weekly
| A13 | Consider regional constraints such as weather, permitting, workforce capabilities, etc.
| A14 | Review plan with wider team to review safety and qualty as a part of the schedule
| A15 | Procurement log up and running & tied to Procore
| A16 | Procurement meetings setup for exterior ASAP
| A17 | Create a 90 day mobilization and project startup plan
| A18 | Begin working on Entitlements and Permitting
People & Teaming - Build the team first!
| B1 | Engage project team as soon as possible and have super on board to begin planning early
| B2 | Design trailers for collaboration, communcation & enjoyement
| B3 | Identify roles by role, scope, and geography
| B4 | Create leaders standard work for all team members
| B5 | Ensure the plan has enough time in the schedule to prevent a crash landing
| B6 | Review GCs/GRs with team before setting the deal
| B7 | Identify project logistics foremen
| B8 | Preconstruction excellence pull plan with team to get organized as soon as possible
| B9 | Create a, "respect for people," plan
| B10 | Begin team balance & health strategy
Winning over the Workforce - Win over hearts and minds
| C1 | Create plan for onsite bathrooms
| C2 | Create plan for onsite lunch room
| C3 | Schedule start of morning huddle systems to train & communcate
| C4 | Make plan for monthly barbeques, Craft feedback and other workforce events & budget
| C5 | Design trailers and interaction areas for worker enjoyement
| C6 | Try to provide workers with 30 minutes in the mornings to setup their day for work
| C7 | Provide smoking areas if possible
| C8 | Provide good parking if possible
| C9 | Provide accessible potable water and ice machines
| C10 | Decide to decorate for holiday and make work fun
Contracts & Costs for Culture - Buyout behaviors needed on site
| D1 | Modify all attachments to work orders to drive behaviors
| D2 | Track all needed contract inclusions for site logistics and operations with estimators
| D3 | Buyout coordination efforts that will predict schedule success (In-wall Coordination, BIM, Prefab, etc.)
| D4 | Buyout just in time procurement
| D5 | Buyout the last planner system and lean methodologies
| D6 | Ensure items about zero tolerance systems are included in contracts
Schedule Health & Right Detail - Maintain a schedule as a tool
| E1 | Detail out all remaining portions of the project
| E2 | Enter lift drawings, BIM & other coordination into the plan
| E3 | Detail out MEP, Startup, Commissioning, Balancing, LS Testing, & FP Testing
| E4 | Review and update schedule for schedule health per checklist
| E5 | Perform an Acumen Fuse analysis and update schedule
| E6 | Identify plan for level of detail to be shown throughout the schedule process
| E7 | Setup pull planning sessions to map out detail at the right times
Risk Analysis - Widen the circle and prevent risk by seeing the future
| F1 | Use template p6 file for new schedules
| F2 | Maintain a basis of schedule
| F3 | Maintain sequence and flow maps
| F4 | Get trade partner input and buyin for the schedule when possible
| F5 | Use production rates for activities that do not have trade input
| F6 | Agree on milestones with wider team & Owner
| F7 | Perform schedule risk analysis for proposed baseline
| F8 | Hold fresh eyes risk meeting with team
| F9 | Establish baseline with Owner
| F10 | Backup schedule monthly in pdf, to .xer, and baseline
| F11 | Perform schedule health survey monthly
| F12 | Establish Owner interface and management strategy
Communicate | The Schedule Tool - Create a system to trigger key actions daily
Begin the weekly update process
Maintain a single project schedule from pursuit to closeout
Review weekly in procurement meeting
Schedule permitting for AHJs
Schedule JHAs and Quality meetings
Clarity & Alignment - Your schedule is as good as you can communicate it
Send out weekly schedule updates
Review in team meetings
Send out notices to contractors weekly
Create schedule visuals
Update WWP maps
Update executive summary plan in conference room
Create schedules all workers can see and understand
Create project signage plan
Lead effective meetings and effective weekly meeting schedules
Mini Marches - Keep the team marching forward in small, incremental steps
Keep an updated 1/3 point and 2/3 point milestone board for the team to work towards
Consider using SCRUM boards for milestones
Consider monthly or weekly schedule snapshots to guide project participants of intermediate goals
Create schedule visual outlining individual contractor's work
Pull plan all milestones and use for weekly work planning and day planning
Interface w/ Owner - Shield the field from variation and get the time and money we need
Create monthly schedule narrative and begin sending monthly
Create fragnets with a, "time impact analysis, when changes occur
Perform a change order analysis when changes occur
Ensure schedule additions will not derail the project team or trade partners
Maintain area maps showing changes and end dates
Review schedule with Owner weekly
Idenity substantial and final completion definitions and track deviations due to changes
Stabilize | Balance & Stability - Create stable environments on the project
Create a plan for all inspections onsite
Create a plan for ISLM, Impact Control Planning, and MOPs
Create a plan for deliveries onsite
Plan control of crane and material hoist
Make a plan to control the location of all materials onsite
Organize parking
Organize trailer and field systems
Plan visual management onsite
Create zero tolerance systems
Create incentive systems onsite
Begin project grading systems
Post circle of trust, A-player signs, and F-player signs
Incentive & Survival - Drive accountability and incentivize
Sustaining the Culture - You can't manage what you don’t measure
Cleanliness & Organization - Begin this as the basis of all other successes
The Last Planner System - Get trade partner commitments
Educate last planners through lean training
Align all short interval planning with milestones in master schedule
Phase plan all major phases with trade contractors
Pull plan to all milestones
Utilize make ready printouts to plan for roadblocks, materials, and manpower
Print look-ahead schedules for foremen onsite
Begin weekly work planning process
Begin daily work planning process
WWP
Day Plan
Fanatically remove roadblocks in every meeting